## Project Estimator
Based on https://jacobian.org/2021/may/25/my-estimation-technique/
Project Name
| Task Name | Complexity | Uncertainty | Best Case (days) | Worst Case (days)
| Refactor the doodad | small | low | 1 | 1.1
| Swizzle columns | large | moderate | 5 | 7.5
| Reticulate splines | medium | extreme | 3 | 15
| Reverse manifold intake | medium | moderate | 3 | 4.5
| Deploy | small | low | 1 | 1.1
|  |  |  | 13 | 29.2

## Constants
Complexity | Time (work days) | Uncertainty | Multiplier
large | 5 | extreme | 5
medium | 3 | high | 2
small | 1 | low | 1.1
x-large | 10 | moderate | 1.5